## Sheet1
Fill in your anticipated dates here and work out when you will be able to graduate
| Estimates | Enter your estimates here
| Thesis start date | 2016-07-01
| Number of months to work on your thesis | 6 | months
| Student makes changes to thesis after (STEP 1) feedback | 4 | weeks
| Time taken for student to make revisions to thesis after defence | 6 | weeks
| Time taken for supervisor to review and confirm changes to thesis | 1 | weeks
Expected dates of completion for each stage
No. | Step | Estimate
1 | Set up committee & create thesis plan. | 2016-07-01
2 | Months taken to complete thesis | 6 | months
3 | Submit draft of thesis to final committee meeting | 2017-01-03
4 | Committee review document (STEP 1) | 4 | weeks
5 | Student makes changes to update thesis | 2017-02-28
6 | Thesis Examining Committee review thesis (STEP 2) ready for defence | 6 | weeks
7 | Defence held | 2017-04-05
8 | Student makes revisions for thesis | 2017-05-17
9 | Following supervisor approval thesis submitted to Graduate Studies | 2017-05-24
10 | Graduate Studies approves thesis | 3 | days
11 | Student completes M.Ed. Program completion form and sends convocation form to G.S. | 3 | days
| Estimated Program completion date | 2017-05-30
| Term you will graduate in if you complete your thesis | Term
| By May 10th | Winter term 2018
| By Sept 10th | Summer term 2018
| By Jan 10th | Fall term 2018
Formulas:
Estimate = C13+31*[Estimate, row above]
Estimate = C15+(C6+[Estimate, row above])*7
Update your estimated timescales here
To Find out your estimated program completiuon date